## Sheet1
Task | Start Date | End Date | Duration
Project initiation | 2023-08-20 | 2023-09-01 | 12
Set up development environment | 2023-09-02 | 2023-09-20 | 18
Test noise removal with synthetic noise images | 2023-10-01 | 2023-10-15 | 14
Validate results | 2023-10-18 | 2023-10-30 | 12
Combine steps and test complete algorithm | 2023-11-01 | 2023-11-08 | 7
Overall algorithm testing and optimization | 2023-11-14 | 2023-11-15 | 1
Documentation and reporting | 2023-11-16 | 2023-11-22 | 6
Evaluation and Comparison | 2023-12-12 | 2023-12-20 | 8